## BloodyFast Status Doc
PTS | Test |  | Testable | Status | Progress: | Tester | Time
81.36%
5 | Functionality | Check all the links | 100% | Failed | 100% | Ema | 1
5 |  | Test forms on all pages | 80% | Failed | 100% |  | 2
1 |  | Cookies Testing | 100% | Failed | 100% |  | 1
2 |  | Validate your HTML/CSS | 100% | Passed | 100% |  | 0.5
4 |  | Database testing | 100% | Passed | 100% |  | 0.5
5 | Compatibility | Browser compatibility | 80% | Failed | 80% |  | 2
3 |  | OS compatibility | 100% | Could not test | 40% |  | 0.5
4 |  | Mobile browsing | 100% | Passed | 100% |  | 1
1 |  | Printing options | 100% | Passed | 100% |  | 0.5
4 | Usability | Test for navigation | 90% | Passed | 100% |  | 1
4 |  | Content checking | 100% | Failed | 100% |  | 2
2 |  | Other user information for user help | 100% | Failed | 100% |  | 0.5
4 | Interface | Web server and application server interface | 100% | Passed | 100% |  | 1
3 |  | Application server and Database server interface | 100% | Failed | 100% |  | 1
2 | Security - identify potential vulnerabilities |  | 100% | Failed | 100% |  | 1
2 | Performance | Connection Speed | 0% | To Be Performed | 0%
2 |  | Load | 0% | To Be Performed | 0%
3 |  | Stress | 0% | To Be Performed | 0%
5 | Automation - scripts for: | Donor pages | 100% | Passed | 100% |  | 4
5 |  | Doctor pages | 70% | Passed | 100% |  | 4
5 |  | Staff pages | 80% | Passed | 100% |  | 4
3 | Documentation - Quick Check |  | 90% | In Progress | 70% |  | 2 + 4